## Gantt Chart - Final Year Projec
PROJECT: ANN In Fault Detection of Induction Machines
Project Phase I : 7th Semester
Project Group 11
Project Guide:
Dr. Bindu CJ | [7 empty] | Plan duration | Start | End | Beyond actual plan
Project Start Date: 3 Oct 2023
[8 empty] | 2023 | [19 empty] | 2024
[8 empty] | September |  |  |  |  | October |  |  |  |  | November |  |  |  |  | December |  |  |  |  | January |  |  |  |  | February |  |  |  |  | March |  |  |  |  | April |  |  |  |  | May
| 0 | [6 empty] | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4
[8 empty] | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4
Goals | Category | Assigned to | Progress | Start | Week | Days | PERCENT COMPLETE
Project Development
Fault Conditions | Goal | Juan Thomas | 25% | 2023-10-03 | Week 1 | 7 | 100% | bar: September 5 W5 to October 2 W2
Fault Detection | Goal | Riya Elsa | 25% | 2023-10-03 | Week 1 | 7 | 100% | bar: September 5 W5 to October 2 W2
Operating Conditions of 3 Phase Induction Machines | Goal | Sidharth P | 30% | 2023-10-03 | Week 1 | 7 | 100% | bar: September 5 W5 to October 1 W1
ANN and Neural Networks | Goal | Smriti | 30% | 2023-10-03 | Week 1 | 7 | 100% | bar: September 5 W5 to October 2 W2
Review Meeting | Milestone | All | 0% | 2023-10-10 | Week 2 | 1 | 100% | bar: October 1 W1
Creating a Matlab Model for Fault Conditions
Listing Out Different Fault Conditions and methods of detection | Goal | Juan, Sidharth |  | 2023-10-13 | Week 2 | 10 | 80% | bar: October 2 W2 to October 3 W3
ANN methods to integrate into the model | Goal | Riya, Smriti |  | 2023-10-13 | Week 2 | 15 | 60% | bar: October 2 W2 to October 4 W4
Review Meeting |  | All |  | 2023-11-06 |  | 1 | 100% | bar: November 2 W2
Obtaining Structuring Data | Goal | All |  | 2023-11-13 | Week 2 | 5 | 20% | bar: November 2 W2
Creating Model and simulating for different fault conditions | Goal | All |  | 2023-11-25 | Week 4 | 10
Observations from Model | Milestone | All |  | 2023-12-05 | Week 5 | 5
ANN Integration into Induction Machines
Possibility Study | Goal | Sidharth,Juan |  | 2023-11-25 | Week 8 | 20
Analysing different models | Goal | All |  | 2023-12-15 | Week 11 | 15
Choosing an ideal parameters to implement for our model | Milestone | Riya, Smriti |  | 2023-12-30 | Week 13 | 10
Testing - Phase 2
Developing the Model | Goal |  |  | 2024-02-02 | Week 18 | 15
System test | Goal |  |  | 2024-02-16 | Week 20 | 15
Issues/bugs | Goal |  |  | 2024-03-01 | Week 22 | 15
Completion of Literature Survey | Goal |  |  | 2024-04-04 | Week 27 | 30
Final Report and Publication in IEEE | Milestone |  |  | 2024-05-20 | Week 34 | 30
Formulas:
Start = [Start, row above]+14